## MD Decisions
1. MD Decisions
Project code | S25WRJ01 |  | Open decisions | 3
Review date | 2026-09-20 |  | Results overdue | 1
Enter data below. Blue text = editable. Grey cells = calculated. Dates: dd-mmm-yy. Money: INR lakh.
Keep stable IDs. Blank means unknown; enter zero only if confirmed. Filter the table separately from the project selector.
FICTIONAL TEST DATA — all records and values are invented solely for system testing.
Test review date: 20-Sep-2026. September dates are scenario dates, not real commitments. Replace these records before live use.
Review Meeting Ref = Monthly / Weekly / Daily. Financial Impact is a separate reported amount; do not add overlapping exposures.
Project code | Site / location | Decision ID | Review Meeting Ref | Review Meeting Date | Issue / blocker | Impact if unresolved | Decision / support required | Recommended action | Responsible owner | Financial Impact (INR lakh) | Result due date | Status | MD decision / direction | Last updated | Source / entry notes
S25WRJ01 | P1-SITE-1 | S25WRJ01-DEC-01 | Daily | 2026-09-10 | Concrete pump availability | Delay to foundation pour | Approve pump hire | Release the identified constraint and review output within two days. | Demo Construction Lead P1 | 15 | 2026-09-12 | Closed | Demo approval given; execution completed. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-2 | S25WRJ01-DEC-02 | Weekly | 2026-09-15 | Vendor release awaiting cash allocation | Material delivery slips by five days | Approve phased vendor payment | Release the identified constraint and review output within two days. | Demo Finance Lead P1 | 20 | 2026-09-18 | Under execution | Demo release approved; track delivery daily. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-1 | S25WRJ01-DEC-03 | Monthly | 2026-09-18 | Drawing revision awaiting decision | Ready front remains idle | Approve revised design route | Release the identified constraint and review output within two days. | Demo Engineering Lead P1 | 25 | 2026-09-24 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-2 | S25WRJ01-DEC-04 | Weekly | 2026-09-20 | Recovery crew mobilisation | Weekly output below target | Approve crew transfer | Release the identified constraint and review output within two days. | Demo Project Head P1 | 30 | 2026-09-28 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-1 | S25WJH01-DEC-01 | Daily | 2026-09-10 | Concrete pump availability | Delay to foundation pour | Approve pump hire | Release the identified constraint and review output within two days. | Demo Construction Lead P2 | 25 | 2026-09-12 | Closed | Demo approval given; execution completed. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-2 | S25WJH01-DEC-02 | Weekly | 2026-09-15 | Vendor release awaiting cash allocation | Material delivery slips by five days | Approve phased vendor payment | Release the identified constraint and review output within two days. | Demo Finance Lead P2 | 30 | 2026-09-18 | Under execution | Demo release approved; track delivery daily. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-1 | S25WJH01-DEC-03 | Monthly | 2026-09-18 | Drawing revision awaiting decision | Ready front remains idle | Approve revised design route | Release the identified constraint and review output within two days. | Demo Engineering Lead P2 | 35 | 2026-09-24 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-2 | S25WJH01-DEC-04 | Weekly | 2026-09-20 | Recovery crew mobilisation | Weekly output below target | Approve crew transfer | Release the identified constraint and review output within two days. | Demo Project Head P2 | 40 | 2026-09-28 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-1 | S25WMP01-DEC-01 | Daily | 2026-09-10 | Concrete pump availability | Delay to foundation pour | Approve pump hire | Release the identified constraint and review output within two days. | Demo Construction Lead P3 | 35 | 2026-09-12 | Closed | Demo approval given; execution completed. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-2 | S25WMP01-DEC-02 | Weekly | 2026-09-15 | Vendor release awaiting cash allocation | Material delivery slips by five days | Approve phased vendor payment | Release the identified constraint and review output within two days. | Demo Finance Lead P3 | 40 | 2026-09-18 | Under execution | Demo release approved; track delivery daily. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-1 | S25WMP01-DEC-03 | Monthly | 2026-09-18 | Drawing revision awaiting decision | Ready front remains idle | Approve revised design route | Release the identified constraint and review output within two days. | Demo Engineering Lead P3 | 45 | 2026-09-24 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-2 | S25WMP01-DEC-04 | Weekly | 2026-09-20 | Recovery crew mobilisation | Weekly output below target | Approve crew transfer | Release the identified constraint and review output within two days. | Demo Project Head P3 | 50 | 2026-09-28 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-1 | S26BBI01-DEC-01 | Daily | 2026-09-10 | Concrete pump availability | Delay to foundation pour | Approve pump hire | Release the identified constraint and review output within two days. | Demo Construction Lead P4 | 45 | 2026-09-12 | Closed | Demo approval given; execution completed. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-2 | S26BBI01-DEC-02 | Weekly | 2026-09-15 | Vendor release awaiting cash allocation | Material delivery slips by five days | Approve phased vendor payment | Release the identified constraint and review output within two days. | Demo Finance Lead P4 | 50 | 2026-09-18 | Under execution | Demo release approved; track delivery daily. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-1 | S26BBI01-DEC-03 | Monthly | 2026-09-18 | Drawing revision awaiting decision | Ready front remains idle | Approve revised design route | Release the identified constraint and review output within two days. | Demo Engineering Lead P4 | 55 | 2026-09-24 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-2 | S26BBI01-DEC-04 | Weekly | 2026-09-20 | Recovery crew mobilisation | Weekly output below target | Approve crew transfer | Release the identified constraint and review output within two days. | Demo Project Head P4 | 60 | 2026-09-28 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-1 | S26PRJ01-DEC-01 | Daily | 2026-09-10 | Concrete pump availability | Delay to foundation pour | Approve pump hire | Release the identified constraint and review output within two days. | Demo Construction Lead P5 | 55 | 2026-09-12 | Closed | Demo approval given; execution completed. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-2 | S26PRJ01-DEC-02 | Weekly | 2026-09-15 | Vendor release awaiting cash allocation | Material delivery slips by five days | Approve phased vendor payment | Release the identified constraint and review output within two days. | Demo Finance Lead P5 | 60 | 2026-09-18 | Under execution | Demo release approved; track delivery daily. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-1 | S26PRJ01-DEC-03 | Monthly | 2026-09-18 | Drawing revision awaiting decision | Ready front remains idle | Approve revised design route | Release the identified constraint and review output within two days. | Demo Engineering Lead P5 | 65 | 2026-09-24 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-2 | S26PRJ01-DEC-04 | Weekly | 2026-09-20 | Recovery crew mobilisation | Weekly output below target | Approve crew transfer | Release the identified constraint and review output within two days. | Demo Project Head P5 | 70 | 2026-09-28 | Awaiting decision | Demo decision awaited; recommendation submitted. | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.

## Project Status & EVM
2. Project Status & EVM
Project registry | One current row per project
Review date | 2026-09-20
Enter data below. Blue text = editable. Grey cells = calculated. Dates: dd-mmm-yy. Money: INR lakh.
Keep stable IDs. Blank means unknown; enter zero only if confirmed. Filter the table separately from the project selector.
FICTIONAL TEST DATA — all records and values are invented solely for system testing.
Test review date: 20-Sep-2026. September dates are scenario dates, not real commitments. Replace these records before live use.
FICTIONAL EVM inputs: ratios exercise over-budget, under-budget and on-budget cases. Unverified means not real project evidence.
EAC = BAC / CPI assumes current cost performance continues. Schedule variance is value in INR lakh, not days.
Goal month applies to Goals 1–5. Goal completion is a percentage. Leave unused goals blank. Keep reporting and EVM dates distinct.
Project code | Project name | Sites / locations covered | Project head | Reporting date | Contract value (INR lakh) | Overall planned progress | Overall actual progress | Engineering planned progress | Engineering actual progress | Procurement planned progress | Procurement actual progress | Construction planned progress | Construction actual progress | Original contractual completion | Latest approved completion | Forecast completion | EOT requested up to | EOT status | Next critical milestone | Milestone planned date | Milestone forecast date | Main reason for slippage | Goal month | Project Goal 1 | Goal 1 Status | Goal 1 Completion | Project Goal 2 | Goal 2 Status | Goal 2 Completion | Project Goal 3 | Goal 3 Status | Goal 3 Completion | Project Goal 4 | Goal 4 Status | Goal 4 Completion | Project Goal 5 | Goal 5 Status | Goal 5 Completion | EVM reporting date | BAC approved cost budget (INR lakh) | PV planned value (INR lakh) | EV earned value (INR lakh) | AC actual cost (INR lakh) | CPI cost performance index | SPI schedule performance index | Cost variance (INR lakh) | Schedule variance (INR lakh) | EAC forecast final cost (INR lakh) | ETC forecast remaining cost (INR lakh) | VAC budget less forecast cost (INR lakh) | EVM validation status | Budget reference / EV measurement basis | Reason for EVM variance | EVM corrective action | EVM responsible owner | EVM action due date | Last updated | Source / entry notes
S25WRJ01 | Kekri Sarwar WSP | P1-SITE-1 and P1-SITE-2 | Demo Project Head P1 | 2026-09-20 | 36000 | 70% | 55% | 95% | 90% | 75% | 65% | 60% | 40% | 2027-06-30 | 2027-09-30 | 2027-12-31 | 2027-12-31 | Under review | Complete Pump house civil works | 2026-09-28 | 2026-10-05 | Demo: drawing release and mobilisation below plan. | 2026-09-01 | Complete first concrete pour | Amber | 75% | Approve critical drawings | Red | 40% | Deliver pump package | Green | 90% | Certify September RA bill | Amber | 60% | Mobilise recovery crew | Green | 100% | 2026-09-20 | 30000 | 18000 | 15000 | 17000 | 0.88235 | 0.83333 | -2000 | -3000 | 34000 | 17000 | -4000 | Unverified | DEMO-BASELINE-P1. Illustrative cost-based PV/EV, measured on the same basis as BAC and AC. | Demo resource inefficiency and rework. | Review shift output and reduce rework. | Demo Planning Lead P1 | 2026-09-25 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | Konar Irrigation | P2-SITE-1 and P2-SITE-2 | Demo Project Head P2 | 2026-09-20 | 28800 | 55% | 58% | 80% | 85% | 60% | 68% | 45% | 47% | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 | Not required | Complete Cross regulator civil works | 2026-09-28 | 2026-09-28 | Demo: no current slippage; maintain output. | 2026-09-01 | Complete first concrete pour | Red | 40% | Approve critical drawings | Green | 90% | Deliver pump package | Amber | 60% | Certify September RA bill | Green | 100% | Mobilise recovery crew | Amber | 75% | 2026-09-20 | 24000 | 12000 | 13000 | 12000 | 1.0833 | 1.0833 | 1000 | 1000 | 22153.8462 | 10153.8462 | 1846.1538 | Unverified | DEMO-BASELINE-P2. Illustrative cost-based PV/EV, measured on the same basis as BAC and AC. | Demo productivity ahead of budget. | Maintain planned resource mix and weekly review. | Demo Planning Lead P2 | 2026-09-25 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | Indore WSP | P3-SITE-1 and P3-SITE-2 | Demo Project Head P3 | 2026-09-20 | 21600 | 65% | 65% | 90% | 90% | 70% | 70% | 50% | 50% | 2027-06-30 | 2027-09-30 | 2027-06-30 | 2027-12-31 | Under review | Complete Pump house civil works | 2026-09-28 | 2026-09-28 | Demo: no current slippage; maintain output. | 2026-09-01 | Complete first concrete pour | Green | 90% | Approve critical drawings | Amber | 60% | Deliver pump package | Green | 100% | Certify September RA bill | Amber | 75% | Mobilise recovery crew | Red | 40% | 2026-09-20 | 18000 | 10000 | 10000 | 10000 | 1 | 1 | 0 | 0 | 18000 | 8000 | 0 | Unverified | DEMO-BASELINE-P3. Illustrative cost-based PV/EV, measured on the same basis as BAC and AC. | Demo case at planned cost and schedule. | Maintain planned resource mix and weekly review. | Demo Planning Lead P3 | 2026-09-25 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | NTPC Barauni | P4-SITE-1 and P4-SITE-2 | Demo Project Head P4 | 2026-09-20 | 26400 | 30% | 24% | 70% | 60% | 35% | 25% | 15% | 10% | 2027-06-30 | 2027-06-30 | 2027-10-31 | 2027-06-30 | Not required | Complete Pump foundation civil works | 2026-09-28 | 2026-10-05 | Demo: drawing release and mobilisation below plan. | 2026-09-01 | Complete first concrete pour | Amber | 60% | Approve critical drawings | Green | 100% | Deliver pump package | Amber | 75% | Certify September RA bill | Red | 40% | Mobilise recovery crew | Green | 90% | 2026-09-20 | 22000 | 6000 | 4500 | 5500 | 0.81818 | 0.75 | -1000 | -1500 | 26888.8889 | 21388.8889 | -4888.8889 | Unverified | DEMO-BASELINE-P4. Illustrative cost-based PV/EV, measured on the same basis as BAC and AC. | Demo resource inefficiency and rework. | Review shift output and reduce rework. | Demo Planning Lead P4 | 2026-09-25 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | RRVPNL Dahara | P5-SITE-1 and P5-SITE-2 | Demo Project Head P5 | 2026-09-20 | 19200 | 25% | 28% | 60% | 70% | 25% | 30% | 10% | 12% | 2027-06-30 | 2027-09-30 | 2027-06-30 | 2027-12-31 | Under review | Complete Control room civil works | 2026-09-28 | 2026-09-28 | Demo: no current slippage; maintain output. | 2026-09-01 | Complete first concrete pour | Green | 100% | Approve critical drawings | Amber | 75% | Deliver pump package | Red | 40% | Certify September RA bill | Green | 90% | Mobilise recovery crew | Amber | 60% | 2026-09-20 | 16000 | 4000 | 4600 | 4200 | 1.0952 | 1.15 | 400 | 600 | 14608.6957 | 10408.6957 | 1391.3043 | Unverified | DEMO-BASELINE-P5. Illustrative cost-based PV/EV, measured on the same basis as BAC and AC. | Demo productivity ahead of budget. | Maintain planned resource mix and weekly review. | Demo Planning Lead P5 | 2026-09-25 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.

## Construction & Resources
3. Construction & Resources
Project code | S25WRJ01 |  | Construction plan | 60% |  | Labour planned | 155 |  |  | Batching plant | Ajax | Excavator | Miller | Truck / dumper | Tractor / breaker | JCB | Other machines
Deployment as of | 2026-09-20 |  | Construction actual | 40% |  | Labour actual | 135 |  |  | 2 | 2 | 5 | 2 | 7 | 2 | 2 | 2
|  |  | Progress as of | 2026-09-20 |  | Listed machines | 24
Enter data below. Blue text = editable. Grey cells = calculated. Dates: dd-mmm-yy. Money: INR lakh.
Keep stable IDs. Blank means unknown; enter zero only if confirmed. Filter the table separately from the project selector.
FICTIONAL TEST DATA — all records and values are invented solely for system testing.
Test review date: 20-Sep-2026. September dates are scenario dates, not real commitments. Replace these records before live use.
Labour and machinery summaries use the dated project/site snapshots at row 227; activity allocations are not added again.
Deployment summaries add two distinct site snapshots per project as of 20-Sep-2026. Activity labour is not added again.
Resources requiring intervention: enter only the critical resources. Separate several resource names with commas; no macros are used.
RMC/Ajax, Hydra/Crane, Excavator, JCB, Truck/Dumper, Tractor, De-Watering Pump, Concrete Pump, Small Tools, Shuttering, Scaffolding
Project code | Site / location | Plan Month | Front / activity ID | Work front / structure | Activity | Week starting | Unit | Weekly target quantity | Actual quantity achieved | Shortfall quantity | Quantity ready for execution | Labour deployed - Planned | Labour deployed - Actual | Drawing Approval Status | Contractor Deployment Status | Planned Contractor Deployment | Actual Contractor Deployment | Shuttering Availability Status | Steel Availability Status | Steel Required | Steel Available | Steel Unit | Front readiness | Pending prerequisite | Reason for low / no execution | Resources requiring intervention | Shortage / support required | Recovery action required | Additional funds required (INR lakh) | Responsible owner | Committed execution date | Expected weekly output after action | Linked Decision ID | Last updated | Source / entry notes
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-ACT-01 | Clear water reservoir | RCC concreting | 2026-09-07 | m3 | 200 | 200 | 0 | 200 | 30 | 30 | YES | YES | 2026-09-05 | 2026-09-05 | YES | YES | 20 | 20 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Target achieved. | Concrete Pump | No current shortage; resolved test item. | Close action and retain productivity record. | 0 | Demo Construction Lead P1 | 2026-09-08 | 200 | S25WRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-2 | 2026-09-01 | S25WRJ01-ACT-02 | Pipe corridor | RCC concreting | 2026-09-14 | m3 | 220 | 143 | 77 | 220 | 35 | 35 | YES | YES | 2026-09-12 | 2026-09-13 | YES | YES | 25 | 25 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Pump downtime reduced output. | RMC/Ajax, Concrete Pump | One standby concrete pump required. | Mobilise the listed resource and confirm readiness before start. | 15 | Demo Construction Lead P1 | 2026-09-15 | 220 | S25WRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-ACT-03 | Pump house | RCC concreting | 2026-09-21 | m3 | 240 | 0 | 240 | 120 | 40 | 22 | NO | NO | 2026-09-19 | Not yet occurred | NO | NO | 30 | 12 | tonnes | Blocked | Approved drawing and reinforcement delivery. | Future week; execution has not started. | Shuttering, Hydra/Crane | Mobilise one crane and 150 m2 shuttering. | Mobilise the listed resource and confirm readiness before start. | 20 | Demo Construction Lead P1 | 2026-09-22 | 240 | S25WRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-2 | 2026-09-01 | S25WRJ01-ACT-04 | Treatment plant | Earth excavation | 2026-09-28 | m3 | 260 | 0 | 260 | 260 | 45 | 45 | YES | YES | 2026-09-24 | 2026-09-18 | NA | NA | 0 | 0 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Future week; execution has not started. | Excavator, Truck/Dumper | Reserve one excavator and two dumpers. | Mobilise the listed resource and confirm readiness before start. | 25 | Demo Construction Lead P1 | 2026-09-29 | 260 | S25WRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-ACT-01 | Canal headworks | RCC concreting | 2026-09-07 | m3 | 225 | 225 | 0 | 225 | 32 | 32 | YES | YES | 2026-09-05 | 2026-09-05 | YES | YES | 20 | 20 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Target achieved. | Concrete Pump | No current shortage; resolved test item. | Close action and retain productivity record. | 0 | Demo Construction Lead P2 | 2026-09-08 | 225 | S25WJH01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-2 | 2026-09-01 | S25WJH01-ACT-02 | Canal reach | RCC concreting | 2026-09-14 | m3 | 245 | 159 | 86 | 245 | 37 | 37 | YES | YES | 2026-09-12 | 2026-09-13 | YES | YES | 25 | 25 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Pump downtime reduced output. | RMC/Ajax, Concrete Pump | One standby concrete pump required. | Mobilise the listed resource and confirm readiness before start. | 15 | Demo Construction Lead P2 | 2026-09-15 | 245 | S25WJH01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-ACT-03 | Cross regulator | RCC concreting | 2026-09-21 | m3 | 265 | 0 | 265 | 120 | 42 | 22 | NO | NO | 2026-09-19 | Not yet occurred | NO | NO | 30 | 12 | tonnes | Blocked | Approved drawing and reinforcement delivery. | Future week; execution has not started. | Shuttering, Hydra/Crane | Mobilise one crane and 150 m2 shuttering. | Mobilise the listed resource and confirm readiness before start. | 20 | Demo Construction Lead P2 | 2026-09-22 | 265 | S25WJH01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-2 | 2026-09-01 | S25WJH01-ACT-04 | Pump station | Earth excavation | 2026-09-28 | m3 | 285 | 0 | 285 | 285 | 47 | 47 | YES | YES | 2026-09-24 | 2026-09-18 | NA | NA | 0 | 0 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Future week; execution has not started. | Excavator, Truck/Dumper | Reserve one excavator and two dumpers. | Mobilise the listed resource and confirm readiness before start. | 25 | Demo Construction Lead P2 | 2026-09-29 | 285 | S25WJH01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-ACT-01 | Service reservoir | RCC concreting | 2026-09-07 | m3 | 250 | 250 | 0 | 250 | 34 | 34 | YES | YES | 2026-09-05 | 2026-09-05 | YES | YES | 20 | 20 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Target achieved. | Concrete Pump | No current shortage; resolved test item. | Close action and retain productivity record. | 0 | Demo Construction Lead P3 | 2026-09-08 | 250 | S25WMP01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-2 | 2026-09-01 | S25WMP01-ACT-02 | Distribution zone | RCC concreting | 2026-09-14 | m3 | 270 | 176 | 94 | 270 | 39 | 39 | YES | YES | 2026-09-12 | 2026-09-13 | YES | YES | 25 | 25 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Pump downtime reduced output. | RMC/Ajax, Concrete Pump | One standby concrete pump required. | Mobilise the listed resource and confirm readiness before start. | 15 | Demo Construction Lead P3 | 2026-09-15 | 270 | S25WMP01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-ACT-03 | Pump house | RCC concreting | 2026-09-21 | m3 | 290 | 0 | 290 | 120 | 44 | 22 | NO | NO | 2026-09-19 | Not yet occurred | NO | NO | 30 | 12 | tonnes | Blocked | Approved drawing and reinforcement delivery. | Future week; execution has not started. | Shuttering, Hydra/Crane | Mobilise one crane and 150 m2 shuttering. | Mobilise the listed resource and confirm readiness before start. | 20 | Demo Construction Lead P3 | 2026-09-22 | 290 | S25WMP01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-2 | 2026-09-01 | S25WMP01-ACT-04 | Water treatment plant | Earth excavation | 2026-09-28 | m3 | 310 | 0 | 310 | 310 | 49 | 49 | YES | YES | 2026-09-24 | 2026-09-18 | NA | NA | 0 | 0 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Future week; execution has not started. | Excavator, Truck/Dumper | Reserve one excavator and two dumpers. | Mobilise the listed resource and confirm readiness before start. | 25 | Demo Construction Lead P3 | 2026-09-29 | 310 | S25WMP01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-ACT-01 | Cooling water structure | RCC concreting | 2026-09-07 | m3 | 275 | 275 | 0 | 275 | 36 | 36 | YES | YES | 2026-09-05 | 2026-09-05 | YES | YES | 20 | 20 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Target achieved. | Concrete Pump | No current shortage; resolved test item. | Close action and retain productivity record. | 0 | Demo Construction Lead P4 | 2026-09-08 | 275 | S26BBI01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-2 | 2026-09-01 | S26BBI01-ACT-02 | Utility corridor | RCC concreting | 2026-09-14 | m3 | 295 | 192 | 103 | 295 | 41 | 41 | YES | YES | 2026-09-12 | 2026-09-13 | YES | YES | 25 | 25 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Pump downtime reduced output. | RMC/Ajax, Concrete Pump | One standby concrete pump required. | Mobilise the listed resource and confirm readiness before start. | 15 | Demo Construction Lead P4 | 2026-09-15 | 295 | S26BBI01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-ACT-03 | Pump foundation | RCC concreting | 2026-09-21 | m3 | 315 | 0 | 315 | 120 | 46 | 22 | NO | NO | 2026-09-19 | Not yet occurred | NO | NO | 30 | 12 | tonnes | Blocked | Approved drawing and reinforcement delivery. | Future week; execution has not started. | Shuttering, Hydra/Crane | Mobilise one crane and 150 m2 shuttering. | Mobilise the listed resource and confirm readiness before start. | 20 | Demo Construction Lead P4 | 2026-09-22 | 315 | S26BBI01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-2 | 2026-09-01 | S26BBI01-ACT-04 | Service building | Earth excavation | 2026-09-28 | m3 | 335 | 0 | 335 | 335 | 51 | 51 | YES | YES | 2026-09-24 | 2026-09-18 | NA | NA | 0 | 0 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Future week; execution has not started. | Excavator, Truck/Dumper | Reserve one excavator and two dumpers. | Mobilise the listed resource and confirm readiness before start. | 25 | Demo Construction Lead P4 | 2026-09-29 | 335 | S26BBI01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-ACT-01 | Transformer foundation | RCC concreting | 2026-09-07 | m3 | 300 | 300 | 0 | 300 | 38 | 38 | YES | YES | 2026-09-05 | 2026-09-05 | YES | YES | 20 | 20 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Target achieved. | Concrete Pump | No current shortage; resolved test item. | Close action and retain productivity record. | 0 | Demo Construction Lead P5 | 2026-09-08 | 300 | S26PRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-2 | 2026-09-01 | S26PRJ01-ACT-02 | Cable trench | RCC concreting | 2026-09-14 | m3 | 320 | 208 | 112 | 320 | 43 | 43 | YES | YES | 2026-09-12 | 2026-09-13 | YES | YES | 25 | 25 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Pump downtime reduced output. | RMC/Ajax, Concrete Pump | One standby concrete pump required. | Mobilise the listed resource and confirm readiness before start. | 15 | Demo Construction Lead P5 | 2026-09-15 | 320 | S26PRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-ACT-03 | Control room | RCC concreting | 2026-09-21 | m3 | 340 | 0 | 340 | 120 | 48 | 22 | NO | NO | 2026-09-19 | Not yet occurred | NO | NO | 30 | 12 | tonnes | Blocked | Approved drawing and reinforcement delivery. | Future week; execution has not started. | Shuttering, Hydra/Crane | Mobilise one crane and 150 m2 shuttering. | Mobilise the listed resource and confirm readiness before start. | 20 | Demo Construction Lead P5 | 2026-09-22 | 340 | S26PRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-2 | 2026-09-01 | S26PRJ01-ACT-04 | Switchyard road | Earth excavation | 2026-09-28 | m3 | 360 | 0 | 360 | 360 | 53 | 53 | YES | YES | 2026-09-24 | 2026-09-18 | NA | NA | 0 | 0 | tonnes | Ready | None; prerequisites confirmed in this fictional scenario. | Future week; execution has not started. | Excavator, Truck/Dumper | Reserve one excavator and two dumpers. | Mobilise the listed resource and confirm readiness before start. | 25 | Demo Construction Lead P5 | 2026-09-29 | 360 | S26PRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
Project deployment snapshots
One row per project/site/date. Count each worker or machine once. Replace an all-sites row before adding its site breakdown.
Project code | Site / scope | Reporting date | Labour planned | Labour actual | Batching plant | Ajax | Excavator | Miller | Truck / dumper | Tractor / breaker | JCB | Other machines | Snapshot notes
S25WRJ01 | P1-SITE-1 | 2026-09-20 | 75 | 65 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.
S25WRJ01 | P1-SITE-2 | 2026-09-20 | 80 | 70 | 1 | 1 | 3 | 1 | 4 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.
S25WJH01 | P2-SITE-1 | 2026-09-20 | 85 | 77 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.
S25WJH01 | P2-SITE-2 | 2026-09-20 | 90 | 82 | 1 | 1 | 3 | 1 | 4 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.
S25WMP01 | P3-SITE-1 | 2026-09-20 | 95 | 89 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.
S25WMP01 | P3-SITE-2 | 2026-09-20 | 100 | 94 | 1 | 1 | 3 | 1 | 4 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.
S26BBI01 | P4-SITE-1 | 2026-09-20 | 105 | 101 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.
S26BBI01 | P4-SITE-2 | 2026-09-20 | 110 | 106 | 1 | 1 | 3 | 1 | 4 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.
S26PRJ01 | P5-SITE-1 | 2026-09-20 | 115 | 113 | 1 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.
S26PRJ01 | P5-SITE-2 | 2026-09-20 | 120 | 118 | 1 | 1 | 3 | 1 | 4 | 1 | 1 | 1 | FICTIONAL TEST DATA. Distinct people and machines at this site as of 20-Sep-2026.

## Invoicing Status
4. Invoicing Status
Project code | S25WRJ01 |  | Tracked records | 4
Review date | 2026-09-20
Enter data below. Blue text = editable. Grey cells = calculated. Dates: dd-mmm-yy. Money: INR lakh.
Keep stable IDs. Blank means unknown; enter zero only if confirmed. Filter the table separately from the project selector.
FICTIONAL TEST DATA — all records and values are invented solely for system testing.
Test review date: 20-Sep-2026. September dates are scenario dates, not real commitments. Replace these records before live use.
One current row per bill or distinct payable. Present/Next Status share the same dropdown; record a date for the next commitment.
Outstanding is a reported input: confirm deductions, retention and paid-to-date rather than assuming bill amount minus cash.
Project code | Invoice / RA bill reference | Client name | Bill amount (INR lakh) | Submission date | Present Status | Next Status | Next Status Target Date | Expected certification date | Certified amount (INR lakh) | Amount received (INR lakh) | Outstanding balance (INR lakh) | Contractual payment due date | Expected collection date | Reason pending | Action / MD support required | Responsible owner | Linked Decision ID | Last updated | Source / entry notes
S25WRJ01 | S25WRJ01-RA-01 | Demo Client P1 | 400 | 2026-09-02 | Fully collected | Fully collected | 2026-09-15 | 2026-09-08 | 400 | 400 | 0 | 2026-09-18 | 2026-09-15 | None; collected in full. | No further action. | Demo Billing Lead P1 | S25WRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | S25WRJ01-RA-02 | Demo Client P1 | 450 | 2026-09-07 | Part payment received | Fully collected | 2026-09-25 | 2026-09-12 | 450 | 180 | 270 | 2026-09-28 | 2026-09-25 | Balance release under client payment cycle. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P1 | S25WRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | S25WRJ01-RA-03 | Demo Client P1 | 500 | 2026-09-12 | Under certification | Certified | 2026-09-24 | 2026-09-24 | 0 | 0 | 500 | 2026-09-29 | 2026-09-29 | Measurement verification pending. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P1 | S25WRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | S25WRJ01-RA-04 | Demo Client P1 | 550 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-27 | 0 | 0 | 550 | 2026-09-30 | 2026-09-30 | Bill documents under preparation. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P1 | S25WRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | S25WJH01-RA-01 | Demo Client P2 | 500 | 2026-09-02 | Fully collected | Fully collected | 2026-09-15 | 2026-09-08 | 500 | 500 | 0 | 2026-09-18 | 2026-09-15 | None; collected in full. | No further action. | Demo Billing Lead P2 | S25WJH01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | S25WJH01-RA-02 | Demo Client P2 | 550 | 2026-09-07 | Part payment received | Fully collected | 2026-09-25 | 2026-09-12 | 550 | 220 | 330 | 2026-09-28 | 2026-09-25 | Balance release under client payment cycle. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P2 | S25WJH01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | S25WJH01-RA-03 | Demo Client P2 | 600 | 2026-09-12 | Under certification | Certified | 2026-09-24 | 2026-09-24 | 0 | 0 | 600 | 2026-09-29 | 2026-09-29 | Measurement verification pending. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P2 | S25WJH01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | S25WJH01-RA-04 | Demo Client P2 | 650 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-27 | 0 | 0 | 650 | 2026-09-30 | 2026-09-30 | Bill documents under preparation. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P2 | S25WJH01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | S25WMP01-RA-01 | Demo Client P3 | 600 | 2026-09-02 | Fully collected | Fully collected | 2026-09-15 | 2026-09-08 | 600 | 600 | 0 | 2026-09-18 | 2026-09-15 | None; collected in full. | No further action. | Demo Billing Lead P3 | S25WMP01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | S25WMP01-RA-02 | Demo Client P3 | 650 | 2026-09-07 | Part payment received | Fully collected | 2026-09-25 | 2026-09-12 | 650 | 260 | 390 | 2026-09-28 | 2026-09-25 | Balance release under client payment cycle. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P3 | S25WMP01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | S25WMP01-RA-03 | Demo Client P3 | 700 | 2026-09-12 | Under certification | Certified | 2026-09-24 | 2026-09-24 | 0 | 0 | 700 | 2026-09-29 | 2026-09-29 | Measurement verification pending. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P3 | S25WMP01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | S25WMP01-RA-04 | Demo Client P3 | 750 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-27 | 0 | 0 | 750 | 2026-09-30 | 2026-09-30 | Bill documents under preparation. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P3 | S25WMP01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | S26BBI01-RA-01 | Demo Client P4 | 700 | 2026-09-02 | Fully collected | Fully collected | 2026-09-15 | 2026-09-08 | 700 | 700 | 0 | 2026-09-18 | 2026-09-15 | None; collected in full. | No further action. | Demo Billing Lead P4 | S26BBI01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | S26BBI01-RA-02 | Demo Client P4 | 750 | 2026-09-07 | Part payment received | Fully collected | 2026-09-25 | 2026-09-12 | 750 | 300 | 450 | 2026-09-28 | 2026-09-25 | Balance release under client payment cycle. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P4 | S26BBI01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | S26BBI01-RA-03 | Demo Client P4 | 800 | 2026-09-12 | Under certification | Certified | 2026-09-24 | 2026-09-24 | 0 | 0 | 800 | 2026-09-29 | 2026-09-29 | Measurement verification pending. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P4 | S26BBI01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | S26BBI01-RA-04 | Demo Client P4 | 850 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-27 | 0 | 0 | 850 | 2026-09-30 | 2026-09-30 | Bill documents under preparation. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P4 | S26BBI01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | S26PRJ01-RA-01 | Demo Client P5 | 800 | 2026-09-02 | Fully collected | Fully collected | 2026-09-15 | 2026-09-08 | 800 | 800 | 0 | 2026-09-18 | 2026-09-15 | None; collected in full. | No further action. | Demo Billing Lead P5 | S26PRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | S26PRJ01-RA-02 | Demo Client P5 | 850 | 2026-09-07 | Part payment received | Fully collected | 2026-09-25 | 2026-09-12 | 850 | 340 | 510 | 2026-09-28 | 2026-09-25 | Balance release under client payment cycle. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P5 | S26PRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | S26PRJ01-RA-03 | Demo Client P5 | 900 | 2026-09-12 | Under certification | Certified | 2026-09-24 | 2026-09-24 | 0 | 0 | 900 | 2026-09-29 | 2026-09-29 | Measurement verification pending. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P5 | S26PRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | S26PRJ01-RA-04 | Demo Client P5 | 950 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-27 | 0 | 0 | 950 | 2026-09-30 | 2026-09-30 | Bill documents under preparation. | Follow up with client accounts and certify supporting records. | Demo Billing Lead P5 | S26PRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.

## Liability Status
5. Liability Status
Project code | S25WRJ01 |  | Tracked records | 4
Review date | 2026-09-20
Enter data below. Blue text = editable. Grey cells = calculated. Dates: dd-mmm-yy. Money: INR lakh.
Keep stable IDs. Blank means unknown; enter zero only if confirmed. Filter the table separately from the project selector.
FICTIONAL TEST DATA — all records and values are invented solely for system testing.
Test review date: 20-Sep-2026. September dates are scenario dates, not real commitments. Replace these records before live use.
One current row per bill or distinct payable. Present/Next Status share the same dropdown; record a date for the next commitment.
Outstanding is a reported input: confirm deductions, retention and paid-to-date rather than assuming bill amount minus cash.
Fictional contractor and vendor bills include fully paid, partly paid, under-verification and approved-for-payment cases.
Project code | Liability / bill reference | Party type | Contractor / vendor name | Work / supply description | Bill / claim amount (INR lakh) | Bill received date | Present Status | Next Status | Next Status Target Date | Certified / approved amount (INR lakh) | Amount paid (INR lakh) | Outstanding liability (INR lakh) | Contractual payment due date | Expected payment date | Reason pending | Work affected if delayed | Action / MD support required | Responsible owner | Linked Decision ID | Last updated | Source / entry notes
S25WRJ01 | S25WRJ01-PAY-01 | Contractor | Fictional Civil Works P1-1 | Concrete works | 100 | 2026-09-03 | Fully paid | Fully paid | 2026-09-16 | 100 | 100 | 0 | 2026-09-18 | 2026-09-16 | None; settled. | None; item closed. | No further action. | Demo Finance Lead P1 | S25WRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | S25WRJ01-PAY-02 | Vendor | Fictional Supplies P1-2 | Reinforcement supply | 120 | 2026-09-08 | Partly paid | Fully paid | 2026-09-24 | 120 | 60 | 60 | 2026-09-25 | 2026-09-24 | Payment allocation pending. | Next phase of Pipe corridor. | Confirm certification and approve staged payment. | Demo Finance Lead P1 | S25WRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | S25WRJ01-PAY-03 | Contractor | Fictional Civil Works P1-3 | Earthwork | 140 | 2026-09-14 | Under verification | Certified | 2026-09-25 | 0 | 0 | 140 | 2026-09-28 | 2026-09-28 | Quantity reconciliation pending. | Next phase of Pump house. | Confirm certification and approve staged payment. | Demo Finance Lead P1 | S25WRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | S25WRJ01-PAY-04 | Vendor | Fictional Supplies P1-4 | Pump equipment | 160 | 2026-09-18 | Approved for payment | Fully paid | 2026-09-27 | 160 | 0 | 160 | 2026-09-30 | 2026-09-27 | Payment allocation pending. | Next phase of Treatment plant. | Confirm certification and approve staged payment. | Demo Finance Lead P1 | S25WRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | S25WJH01-PAY-01 | Contractor | Fictional Civil Works P2-1 | Concrete works | 130 | 2026-09-03 | Fully paid | Fully paid | 2026-09-16 | 130 | 130 | 0 | 2026-09-18 | 2026-09-16 | None; settled. | None; item closed. | No further action. | Demo Finance Lead P2 | S25WJH01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | S25WJH01-PAY-02 | Vendor | Fictional Supplies P2-2 | Reinforcement supply | 150 | 2026-09-08 | Partly paid | Fully paid | 2026-09-24 | 150 | 75 | 75 | 2026-09-25 | 2026-09-24 | Payment allocation pending. | Next phase of Canal reach. | Confirm certification and approve staged payment. | Demo Finance Lead P2 | S25WJH01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | S25WJH01-PAY-03 | Contractor | Fictional Civil Works P2-3 | Earthwork | 170 | 2026-09-14 | Under verification | Certified | 2026-09-25 | 0 | 0 | 170 | 2026-09-28 | 2026-09-28 | Quantity reconciliation pending. | Next phase of Cross regulator. | Confirm certification and approve staged payment. | Demo Finance Lead P2 | S25WJH01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | S25WJH01-PAY-04 | Vendor | Fictional Supplies P2-4 | Pump equipment | 190 | 2026-09-18 | Approved for payment | Fully paid | 2026-09-27 | 190 | 0 | 190 | 2026-09-30 | 2026-09-27 | Payment allocation pending. | Next phase of Pump station. | Confirm certification and approve staged payment. | Demo Finance Lead P2 | S25WJH01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | S25WMP01-PAY-01 | Contractor | Fictional Civil Works P3-1 | Concrete works | 160 | 2026-09-03 | Fully paid | Fully paid | 2026-09-16 | 160 | 160 | 0 | 2026-09-18 | 2026-09-16 | None; settled. | None; item closed. | No further action. | Demo Finance Lead P3 | S25WMP01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | S25WMP01-PAY-02 | Vendor | Fictional Supplies P3-2 | Reinforcement supply | 180 | 2026-09-08 | Partly paid | Fully paid | 2026-09-24 | 180 | 90 | 90 | 2026-09-25 | 2026-09-24 | Payment allocation pending. | Next phase of Distribution zone. | Confirm certification and approve staged payment. | Demo Finance Lead P3 | S25WMP01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | S25WMP01-PAY-03 | Contractor | Fictional Civil Works P3-3 | Earthwork | 200 | 2026-09-14 | Under verification | Certified | 2026-09-25 | 0 | 0 | 200 | 2026-09-28 | 2026-09-28 | Quantity reconciliation pending. | Next phase of Pump house. | Confirm certification and approve staged payment. | Demo Finance Lead P3 | S25WMP01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | S25WMP01-PAY-04 | Vendor | Fictional Supplies P3-4 | Pump equipment | 220 | 2026-09-18 | Approved for payment | Fully paid | 2026-09-27 | 220 | 0 | 220 | 2026-09-30 | 2026-09-27 | Payment allocation pending. | Next phase of Water treatment plant. | Confirm certification and approve staged payment. | Demo Finance Lead P3 | S25WMP01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | S26BBI01-PAY-01 | Contractor | Fictional Civil Works P4-1 | Concrete works | 190 | 2026-09-03 | Fully paid | Fully paid | 2026-09-16 | 190 | 190 | 0 | 2026-09-18 | 2026-09-16 | None; settled. | None; item closed. | No further action. | Demo Finance Lead P4 | S26BBI01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | S26BBI01-PAY-02 | Vendor | Fictional Supplies P4-2 | Reinforcement supply | 210 | 2026-09-08 | Partly paid | Fully paid | 2026-09-24 | 210 | 105 | 105 | 2026-09-25 | 2026-09-24 | Payment allocation pending. | Next phase of Utility corridor. | Confirm certification and approve staged payment. | Demo Finance Lead P4 | S26BBI01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | S26BBI01-PAY-03 | Contractor | Fictional Civil Works P4-3 | Earthwork | 230 | 2026-09-14 | Under verification | Certified | 2026-09-25 | 0 | 0 | 230 | 2026-09-28 | 2026-09-28 | Quantity reconciliation pending. | Next phase of Pump foundation. | Confirm certification and approve staged payment. | Demo Finance Lead P4 | S26BBI01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | S26BBI01-PAY-04 | Vendor | Fictional Supplies P4-4 | Pump equipment | 250 | 2026-09-18 | Approved for payment | Fully paid | 2026-09-27 | 250 | 0 | 250 | 2026-09-30 | 2026-09-27 | Payment allocation pending. | Next phase of Service building. | Confirm certification and approve staged payment. | Demo Finance Lead P4 | S26BBI01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | S26PRJ01-PAY-01 | Contractor | Fictional Civil Works P5-1 | Concrete works | 220 | 2026-09-03 | Fully paid | Fully paid | 2026-09-16 | 220 | 220 | 0 | 2026-09-18 | 2026-09-16 | None; settled. | None; item closed. | No further action. | Demo Finance Lead P5 | S26PRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | S26PRJ01-PAY-02 | Vendor | Fictional Supplies P5-2 | Reinforcement supply | 240 | 2026-09-08 | Partly paid | Fully paid | 2026-09-24 | 240 | 120 | 120 | 2026-09-25 | 2026-09-24 | Payment allocation pending. | Next phase of Cable trench. | Confirm certification and approve staged payment. | Demo Finance Lead P5 | S26PRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | S26PRJ01-PAY-03 | Contractor | Fictional Civil Works P5-3 | Earthwork | 260 | 2026-09-14 | Under verification | Certified | 2026-09-25 | 0 | 0 | 260 | 2026-09-28 | 2026-09-28 | Quantity reconciliation pending. | Next phase of Control room. | Confirm certification and approve staged payment. | Demo Finance Lead P5 | S26PRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | S26PRJ01-PAY-04 | Vendor | Fictional Supplies P5-4 | Pump equipment | 280 | 2026-09-18 | Approved for payment | Fully paid | 2026-09-27 | 280 | 0 | 280 | 2026-09-30 | 2026-09-27 | Payment allocation pending. | Next phase of Switchyard road. | Confirm certification and approve staged payment. | Demo Finance Lead P5 | S26PRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.

## Engineering Status
6. Engineering Status
Project code | S25WRJ01 |  | Engineering plan | 95% |  | Total drawings | 5 |  | Yet to submit | 2
Review date | 2026-09-20 |  | Engineering actual | 90% |  | Submitted | 3
|  |  | Progress as of | 2026-09-20 |  | Approved | 1
Enter data below. Blue text = editable. Grey cells = calculated. Dates: dd-mmm-yy. Money: INR lakh.
Keep stable IDs. Blank means unknown; enter zero only if confirmed. Filter the table separately from the project selector.
FICTIONAL TEST DATA — all records and values are invented solely for system testing.
Test review date: 20-Sep-2026. September dates are scenario dates, not real commitments. Replace these records before live use.
Counts cover entered unique references only. Use one current row per reference, updating revisions in that row. Red IDs are duplicates.
Submitted includes later stages such as Approved. Each fictional project has 5 drawings: 3 submitted, 1 approved and 2 yet to submit.
Project code | Site / location | Plan Month | Drawing / document reference | Drawing / document description | Linked front / activity ID | Responsible designer / consultant | Required-for-construction date | Planned submission date | Actual submission date | Present Status | Next Status | Next Status Target Date | Expected approval date | Actual approval date | Reason pending / blocker | Work affected if delayed | Action / MD support required | Responsible owner | Linked Decision ID | Last updated | Source / entry notes | Unique reference (calc) | Submitted (calc) | Approved (calc) | Yet to submit (calc)
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-DRG-001 | Clear water reservoir general arrangement | S25WRJ01-ACT-01 | Demo Design Consultant P1 | 2026-09-25 | 2026-09-21 | Not yet occurred | Not started | Under preparation | 2026-09-21 | 2026-09-24 | Not yet occurred | Survey inputs to be issued. | Clear water reservoir execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P1 | S25WRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S25WRJ01 | P1-SITE-2 | 2026-09-01 | S25WRJ01-DRG-002 | Pipe corridor reinforcement detail | S25WRJ01-ACT-02 | Demo Design Consultant P1 | 2026-09-26 | 2026-09-22 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-25 | Not yet occurred | Draft detailing in progress. | Pipe corridor execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P1 | S25WRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-DRG-003 | Pump house foundation section | S25WRJ01-ACT-03 | Demo Design Consultant P1 | 2026-09-27 | 2026-09-12 | 2026-09-12 | Submitted | Under review | 2026-09-23 | 2026-09-26 | Not yet occurred | Review comments and approval pending. | Pump house execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P1 | S25WRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WRJ01 | P1-SITE-2 | 2026-09-01 | S25WRJ01-DRG-004 | Treatment plant equipment layout | S25WRJ01-ACT-04 | Demo Design Consultant P1 | 2026-09-28 | 2026-09-13 | 2026-09-14 | Under review | Approved | 2026-09-25 | 2026-09-25 | Not yet occurred | Review comments and approval pending. | Treatment plant execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P1 | S25WRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-DRG-005 | Clear water reservoir construction detail | S25WRJ01-ACT-01 | Demo Design Consultant P1 | 2026-09-18 | 2026-09-05 | 2026-09-06 | Approved | Approved | 2026-09-16 | 2026-09-16 | 2026-09-16 | None; approved drawing released. | Clear water reservoir execution | No further intervention. | Demo Engineering Lead P1 | S25WRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-DRG-001 | Canal headworks general arrangement | S25WJH01-ACT-01 | Demo Design Consultant P2 | 2026-09-25 | 2026-09-21 | Not yet occurred | Not started | Under preparation | 2026-09-21 | 2026-09-24 | Not yet occurred | Survey inputs to be issued. | Canal headworks execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P2 | S25WJH01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S25WJH01 | P2-SITE-2 | 2026-09-01 | S25WJH01-DRG-002 | Canal reach reinforcement detail | S25WJH01-ACT-02 | Demo Design Consultant P2 | 2026-09-26 | 2026-09-22 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-25 | Not yet occurred | Draft detailing in progress. | Canal reach execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P2 | S25WJH01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-DRG-003 | Cross regulator foundation section | S25WJH01-ACT-03 | Demo Design Consultant P2 | 2026-09-27 | 2026-09-12 | 2026-09-12 | Submitted | Under review | 2026-09-23 | 2026-09-26 | Not yet occurred | Review comments and approval pending. | Cross regulator execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P2 | S25WJH01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WJH01 | P2-SITE-2 | 2026-09-01 | S25WJH01-DRG-004 | Pump station equipment layout | S25WJH01-ACT-04 | Demo Design Consultant P2 | 2026-09-28 | 2026-09-13 | 2026-09-14 | Under review | Approved | 2026-09-25 | 2026-09-25 | Not yet occurred | Review comments and approval pending. | Pump station execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P2 | S25WJH01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-DRG-005 | Canal headworks construction detail | S25WJH01-ACT-01 | Demo Design Consultant P2 | 2026-09-18 | 2026-09-05 | 2026-09-06 | Approved | Approved | 2026-09-16 | 2026-09-16 | 2026-09-16 | None; approved drawing released. | Canal headworks execution | No further intervention. | Demo Engineering Lead P2 | S25WJH01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-DRG-001 | Service reservoir general arrangement | S25WMP01-ACT-01 | Demo Design Consultant P3 | 2026-09-25 | 2026-09-21 | Not yet occurred | Not started | Under preparation | 2026-09-21 | 2026-09-24 | Not yet occurred | Survey inputs to be issued. | Service reservoir execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P3 | S25WMP01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S25WMP01 | P3-SITE-2 | 2026-09-01 | S25WMP01-DRG-002 | Distribution zone reinforcement detail | S25WMP01-ACT-02 | Demo Design Consultant P3 | 2026-09-26 | 2026-09-22 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-25 | Not yet occurred | Draft detailing in progress. | Distribution zone execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P3 | S25WMP01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-DRG-003 | Pump house foundation section | S25WMP01-ACT-03 | Demo Design Consultant P3 | 2026-09-27 | 2026-09-12 | 2026-09-12 | Submitted | Under review | 2026-09-23 | 2026-09-26 | Not yet occurred | Review comments and approval pending. | Pump house execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P3 | S25WMP01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WMP01 | P3-SITE-2 | 2026-09-01 | S25WMP01-DRG-004 | Water treatment plant equipment layout | S25WMP01-ACT-04 | Demo Design Consultant P3 | 2026-09-28 | 2026-09-13 | 2026-09-14 | Under review | Approved | 2026-09-25 | 2026-09-25 | Not yet occurred | Review comments and approval pending. | Water treatment plant execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P3 | S25WMP01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-DRG-005 | Service reservoir construction detail | S25WMP01-ACT-01 | Demo Design Consultant P3 | 2026-09-18 | 2026-09-05 | 2026-09-06 | Approved | Approved | 2026-09-16 | 2026-09-16 | 2026-09-16 | None; approved drawing released. | Service reservoir execution | No further intervention. | Demo Engineering Lead P3 | S25WMP01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-DRG-001 | Cooling water structure general arrangement | S26BBI01-ACT-01 | Demo Design Consultant P4 | 2026-09-25 | 2026-09-21 | Not yet occurred | Not started | Under preparation | 2026-09-21 | 2026-09-24 | Not yet occurred | Survey inputs to be issued. | Cooling water structure execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P4 | S26BBI01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S26BBI01 | P4-SITE-2 | 2026-09-01 | S26BBI01-DRG-002 | Utility corridor reinforcement detail | S26BBI01-ACT-02 | Demo Design Consultant P4 | 2026-09-26 | 2026-09-22 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-25 | Not yet occurred | Draft detailing in progress. | Utility corridor execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P4 | S26BBI01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-DRG-003 | Pump foundation foundation section | S26BBI01-ACT-03 | Demo Design Consultant P4 | 2026-09-27 | 2026-09-12 | 2026-09-12 | Submitted | Under review | 2026-09-23 | 2026-09-26 | Not yet occurred | Review comments and approval pending. | Pump foundation execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P4 | S26BBI01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26BBI01 | P4-SITE-2 | 2026-09-01 | S26BBI01-DRG-004 | Service building equipment layout | S26BBI01-ACT-04 | Demo Design Consultant P4 | 2026-09-28 | 2026-09-13 | 2026-09-14 | Under review | Approved | 2026-09-25 | 2026-09-25 | Not yet occurred | Review comments and approval pending. | Service building execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P4 | S26BBI01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-DRG-005 | Cooling water structure construction detail | S26BBI01-ACT-01 | Demo Design Consultant P4 | 2026-09-18 | 2026-09-05 | 2026-09-06 | Approved | Approved | 2026-09-16 | 2026-09-16 | 2026-09-16 | None; approved drawing released. | Cooling water structure execution | No further intervention. | Demo Engineering Lead P4 | S26BBI01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-DRG-001 | Transformer foundation general arrangement | S26PRJ01-ACT-01 | Demo Design Consultant P5 | 2026-09-25 | 2026-09-21 | Not yet occurred | Not started | Under preparation | 2026-09-21 | 2026-09-24 | Not yet occurred | Survey inputs to be issued. | Transformer foundation execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P5 | S26PRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S26PRJ01 | P5-SITE-2 | 2026-09-01 | S26PRJ01-DRG-002 | Cable trench reinforcement detail | S26PRJ01-ACT-02 | Demo Design Consultant P5 | 2026-09-26 | 2026-09-22 | Not yet occurred | Under preparation | Submitted | 2026-09-22 | 2026-09-25 | Not yet occurred | Draft detailing in progress. | Cable trench execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P5 | S26PRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-DRG-003 | Control room foundation section | S26PRJ01-ACT-03 | Demo Design Consultant P5 | 2026-09-27 | 2026-09-12 | 2026-09-12 | Submitted | Under review | 2026-09-23 | 2026-09-26 | Not yet occurred | Review comments and approval pending. | Control room execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P5 | S26PRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26PRJ01 | P5-SITE-2 | 2026-09-01 | S26PRJ01-DRG-004 | Switchyard road equipment layout | S26PRJ01-ACT-04 | Demo Design Consultant P5 | 2026-09-28 | 2026-09-13 | 2026-09-14 | Under review | Approved | 2026-09-25 | 2026-09-25 | Not yet occurred | Review comments and approval pending. | Switchyard road execution | Confirm design inputs and expedite reviewer response. | Demo Engineering Lead P5 | S26PRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-DRG-005 | Transformer foundation construction detail | S26PRJ01-ACT-01 | Demo Design Consultant P5 | 2026-09-18 | 2026-09-05 | 2026-09-06 | Approved | Approved | 2026-09-16 | 2026-09-16 | 2026-09-16 | None; approved drawing released. | Transformer foundation execution | No further intervention. | Demo Engineering Lead P5 | S26PRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0 | 0

## Procurement Status
7. Procurement Status
Project code | S25WRJ01 |  | Procurement plan | 75% |  | Total packages | 5 |  | Yet to order | 1
Review date | 2026-09-20 |  | Procurement actual | 65% |  | Ordered | 4
|  |  | Progress as of | 2026-09-20 |  | Fully delivered | 1
Enter data below. Blue text = editable. Grey cells = calculated. Dates: dd-mmm-yy. Money: INR lakh.
Keep stable IDs. Blank means unknown; enter zero only if confirmed. Filter the table separately from the project selector.
FICTIONAL TEST DATA — all records and values are invented solely for system testing.
Test review date: 20-Sep-2026. September dates are scenario dates, not real commitments. Replace these records before live use.
Counts cover entered unique references only. Use one current row per reference, updating revisions in that row. Red IDs are duplicates.
Ordered includes later stages such as Partly received. Fully delivered is a subset of Ordered; counts must not be added together.
Project code | Site / location | Plan Month | Procurement package / item ID | Item / package description | Linked front / activity ID | Vendor / supplier | Unit | Total required quantity | Ordered quantity | Quantity received at site | Balance quantity to receive | Required-at-site date | Planned PO date | Actual PO date | Present Status | Next Status | Next Status Target Date | Committed delivery date | Actual final delivery date | Reason pending / blocker | Work affected if delayed | Action / MD support required | Responsible owner | Linked Decision ID | Last updated | Source / entry notes | Unique reference (calc) | Ordered (calc) | Fully delivered (calc) | Yet to order (calc)
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-PKG-001 | Reinforcement lot | S25WRJ01-ACT-01 | Fictional Equipment Supplier P1-1 | tonnes | 100 | 0 | 0 | 100 | 2026-09-30 | 2026-09-22 | Not yet occurred | Requirement finalised | Enquiry issued | 2026-09-22 | 2026-09-30 | Not yet occurred | Enquiry release pending. | Clear water reservoir execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P1 | S25WRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S25WRJ01 | P1-SITE-2 | 2026-09-01 | S25WRJ01-PKG-002 | Pipe fittings lot | S25WRJ01-ACT-02 | Fictional Equipment Supplier P1-2 | numbers | 120 | 120 | 0 | 120 | 2026-09-28 | 2026-09-08 | 2026-09-09 | PO issued | Under manufacturing | 2026-09-23 | 2026-09-28 | Not yet occurred | Vendor manufacturing and inspection sequence. | Pipe corridor execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P1 | S25WRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-PKG-003 | Electrical panels lot | S25WRJ01-ACT-03 | Fictional Equipment Supplier P1-3 | numbers | 140 | 140 | 0 | 140 | 2026-09-29 | 2026-09-07 | 2026-09-07 | Under manufacturing | Inspection pending | 2026-09-24 | 2026-09-29 | Not yet occurred | Vendor manufacturing and inspection sequence. | Pump house execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P1 | S25WRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WRJ01 | P1-SITE-2 | 2026-09-01 | S25WRJ01-PKG-004 | Valve assembly lot | S25WRJ01-ACT-04 | Fictional Equipment Supplier P1-4 | numbers | 160 | 160 | 80 | 80 | 2026-09-25 | 2026-09-05 | 2026-09-05 | Partly received | Fully received | 2026-09-25 | 2026-09-25 | Not yet occurred | Balance consignment in transit. | Treatment plant execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P1 | S25WRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-PKG-005 | Structural steel lot | S25WRJ01-ACT-01 | Fictional Equipment Supplier P1-5 | tonnes | 180 | 180 | 180 | 0 | 2026-09-18 | 2026-09-02 | 2026-09-02 | Fully received | Fully received | 2026-09-17 | 2026-09-17 | 2026-09-17 | None; delivery complete. | Clear water reservoir execution | No further intervention. | Demo Procurement Lead P1 | S25WRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-PKG-001 | Reinforcement lot | S25WJH01-ACT-01 | Fictional Equipment Supplier P2-1 | tonnes | 110 | 0 | 0 | 110 | 2026-09-30 | 2026-09-22 | Not yet occurred | Requirement finalised | Enquiry issued | 2026-09-22 | 2026-09-30 | Not yet occurred | Enquiry release pending. | Canal headworks execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P2 | S25WJH01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S25WJH01 | P2-SITE-2 | 2026-09-01 | S25WJH01-PKG-002 | Pipe fittings lot | S25WJH01-ACT-02 | Fictional Equipment Supplier P2-2 | numbers | 130 | 130 | 0 | 130 | 2026-09-28 | 2026-09-08 | 2026-09-09 | PO issued | Under manufacturing | 2026-09-23 | 2026-09-28 | Not yet occurred | Vendor manufacturing and inspection sequence. | Canal reach execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P2 | S25WJH01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-PKG-003 | Electrical panels lot | S25WJH01-ACT-03 | Fictional Equipment Supplier P2-3 | numbers | 150 | 150 | 0 | 150 | 2026-09-29 | 2026-09-07 | 2026-09-07 | Under manufacturing | Inspection pending | 2026-09-24 | 2026-09-29 | Not yet occurred | Vendor manufacturing and inspection sequence. | Cross regulator execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P2 | S25WJH01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WJH01 | P2-SITE-2 | 2026-09-01 | S25WJH01-PKG-004 | Valve assembly lot | S25WJH01-ACT-04 | Fictional Equipment Supplier P2-4 | numbers | 170 | 170 | 85 | 85 | 2026-09-25 | 2026-09-05 | 2026-09-05 | Partly received | Fully received | 2026-09-25 | 2026-09-25 | Not yet occurred | Balance consignment in transit. | Pump station execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P2 | S25WJH01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-PKG-005 | Structural steel lot | S25WJH01-ACT-01 | Fictional Equipment Supplier P2-5 | tonnes | 190 | 190 | 190 | 0 | 2026-09-18 | 2026-09-02 | 2026-09-02 | Fully received | Fully received | 2026-09-17 | 2026-09-17 | 2026-09-17 | None; delivery complete. | Canal headworks execution | No further intervention. | Demo Procurement Lead P2 | S25WJH01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-PKG-001 | Reinforcement lot | S25WMP01-ACT-01 | Fictional Equipment Supplier P3-1 | tonnes | 120 | 0 | 0 | 120 | 2026-09-30 | 2026-09-22 | Not yet occurred | Requirement finalised | Enquiry issued | 2026-09-22 | 2026-09-30 | Not yet occurred | Enquiry release pending. | Service reservoir execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P3 | S25WMP01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S25WMP01 | P3-SITE-2 | 2026-09-01 | S25WMP01-PKG-002 | Pipe fittings lot | S25WMP01-ACT-02 | Fictional Equipment Supplier P3-2 | numbers | 140 | 140 | 0 | 140 | 2026-09-28 | 2026-09-08 | 2026-09-09 | PO issued | Under manufacturing | 2026-09-23 | 2026-09-28 | Not yet occurred | Vendor manufacturing and inspection sequence. | Distribution zone execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P3 | S25WMP01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-PKG-003 | Electrical panels lot | S25WMP01-ACT-03 | Fictional Equipment Supplier P3-3 | numbers | 160 | 160 | 0 | 160 | 2026-09-29 | 2026-09-07 | 2026-09-07 | Under manufacturing | Inspection pending | 2026-09-24 | 2026-09-29 | Not yet occurred | Vendor manufacturing and inspection sequence. | Pump house execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P3 | S25WMP01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WMP01 | P3-SITE-2 | 2026-09-01 | S25WMP01-PKG-004 | Valve assembly lot | S25WMP01-ACT-04 | Fictional Equipment Supplier P3-4 | numbers | 180 | 180 | 90 | 90 | 2026-09-25 | 2026-09-05 | 2026-09-05 | Partly received | Fully received | 2026-09-25 | 2026-09-25 | Not yet occurred | Balance consignment in transit. | Water treatment plant execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P3 | S25WMP01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-PKG-005 | Structural steel lot | S25WMP01-ACT-01 | Fictional Equipment Supplier P3-5 | tonnes | 200 | 200 | 200 | 0 | 2026-09-18 | 2026-09-02 | 2026-09-02 | Fully received | Fully received | 2026-09-17 | 2026-09-17 | 2026-09-17 | None; delivery complete. | Service reservoir execution | No further intervention. | Demo Procurement Lead P3 | S25WMP01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-PKG-001 | Reinforcement lot | S26BBI01-ACT-01 | Fictional Equipment Supplier P4-1 | tonnes | 130 | 0 | 0 | 130 | 2026-09-30 | 2026-09-22 | Not yet occurred | Requirement finalised | Enquiry issued | 2026-09-22 | 2026-09-30 | Not yet occurred | Enquiry release pending. | Cooling water structure execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P4 | S26BBI01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S26BBI01 | P4-SITE-2 | 2026-09-01 | S26BBI01-PKG-002 | Pipe fittings lot | S26BBI01-ACT-02 | Fictional Equipment Supplier P4-2 | numbers | 150 | 150 | 0 | 150 | 2026-09-28 | 2026-09-08 | 2026-09-09 | PO issued | Under manufacturing | 2026-09-23 | 2026-09-28 | Not yet occurred | Vendor manufacturing and inspection sequence. | Utility corridor execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P4 | S26BBI01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-PKG-003 | Electrical panels lot | S26BBI01-ACT-03 | Fictional Equipment Supplier P4-3 | numbers | 170 | 170 | 0 | 170 | 2026-09-29 | 2026-09-07 | 2026-09-07 | Under manufacturing | Inspection pending | 2026-09-24 | 2026-09-29 | Not yet occurred | Vendor manufacturing and inspection sequence. | Pump foundation execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P4 | S26BBI01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26BBI01 | P4-SITE-2 | 2026-09-01 | S26BBI01-PKG-004 | Valve assembly lot | S26BBI01-ACT-04 | Fictional Equipment Supplier P4-4 | numbers | 190 | 190 | 95 | 95 | 2026-09-25 | 2026-09-05 | 2026-09-05 | Partly received | Fully received | 2026-09-25 | 2026-09-25 | Not yet occurred | Balance consignment in transit. | Service building execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P4 | S26BBI01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-PKG-005 | Structural steel lot | S26BBI01-ACT-01 | Fictional Equipment Supplier P4-5 | tonnes | 210 | 210 | 210 | 0 | 2026-09-18 | 2026-09-02 | 2026-09-02 | Fully received | Fully received | 2026-09-17 | 2026-09-17 | 2026-09-17 | None; delivery complete. | Cooling water structure execution | No further intervention. | Demo Procurement Lead P4 | S26BBI01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-PKG-001 | Reinforcement lot | S26PRJ01-ACT-01 | Fictional Equipment Supplier P5-1 | tonnes | 140 | 0 | 0 | 140 | 2026-09-30 | 2026-09-22 | Not yet occurred | Requirement finalised | Enquiry issued | 2026-09-22 | 2026-09-30 | Not yet occurred | Enquiry release pending. | Transformer foundation execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P5 | S26PRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 0 | 0 | 1
S26PRJ01 | P5-SITE-2 | 2026-09-01 | S26PRJ01-PKG-002 | Pipe fittings lot | S26PRJ01-ACT-02 | Fictional Equipment Supplier P5-2 | numbers | 160 | 160 | 0 | 160 | 2026-09-28 | 2026-09-08 | 2026-09-09 | PO issued | Under manufacturing | 2026-09-23 | 2026-09-28 | Not yet occurred | Vendor manufacturing and inspection sequence. | Cable trench execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P5 | S26PRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-PKG-003 | Electrical panels lot | S26PRJ01-ACT-03 | Fictional Equipment Supplier P5-3 | numbers | 180 | 180 | 0 | 180 | 2026-09-29 | 2026-09-07 | 2026-09-07 | Under manufacturing | Inspection pending | 2026-09-24 | 2026-09-29 | Not yet occurred | Vendor manufacturing and inspection sequence. | Control room execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P5 | S26PRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26PRJ01 | P5-SITE-2 | 2026-09-01 | S26PRJ01-PKG-004 | Valve assembly lot | S26PRJ01-ACT-04 | Fictional Equipment Supplier P5-4 | numbers | 200 | 200 | 100 | 100 | 2026-09-25 | 2026-09-05 | 2026-09-05 | Partly received | Fully received | 2026-09-25 | 2026-09-25 | Not yet occurred | Balance consignment in transit. | Switchyard road execution | Confirm vendor schedule and expedite the next stage. | Demo Procurement Lead P5 | S26PRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 0 | 0
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-PKG-005 | Structural steel lot | S26PRJ01-ACT-01 | Fictional Equipment Supplier P5-5 | tonnes | 220 | 220 | 220 | 0 | 2026-09-18 | 2026-09-02 | 2026-09-02 | Fully received | Fully received | 2026-09-17 | 2026-09-17 | 2026-09-17 | None; delivery complete. | Transformer foundation execution | No further intervention. | Demo Procurement Lead P5 | S26PRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. | 1 | 1 | 1 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0
[27 empty] | 0 | 0 | 0 | 0

## Lookahead Plan
8. Lookahead Plan
Project code | S25WRJ01
Review date | 2026-09-20
Enter data below. Blue text = editable. Grey cells = calculated. Dates: dd-mmm-yy. Money: INR lakh.
Keep stable IDs. Blank means unknown; enter zero only if confirmed. Filter the table separately from the project selector.
FICTIONAL TEST DATA — all records and values are invented solely for system testing.
Test review date: 20-Sep-2026. September dates are scenario dates, not real commitments. Replace these records before live use.
One row per project/activity/week. Actual output remains in Construction & Resources using the same project, activity ID and week.
Red clearance dates indicate a deliberate test conflict: clearance is later than planned start. Actual output is on Construction & Resources.
Project code | Site / location | Plan Month | Front / activity ID | Work front / structure | Planned activity | Week starting | Planned start | Planned finish | Unit | Planned quantity for the week | Execution readiness | Constraint / support required | Constraint owner | Constraint clearance target date | MD support required | Linked Decision ID | Activity owner | Activity status | Last updated | Source / entry notes
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-ACT-01 | Clear water reservoir | RCC concreting | 2026-09-07 | 2026-09-07 | 2026-09-11 | m3 | 200 | Ready | No current shortage; resolved test item. | Demo Construction Lead P1 | 2026-09-06 | No further support; completed. | S25WRJ01-DEC-01 | Demo Site Engineer P1 | Completed | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-2 | 2026-09-01 | S25WRJ01-ACT-02 | Pipe corridor | RCC concreting | 2026-09-14 | 2026-09-14 | 2026-09-18 | m3 | 220 | At risk | One standby concrete pump required. | Demo Construction Lead P1 | 2026-09-13 | Mobilise the listed resource and confirm readiness before start. | S25WRJ01-DEC-02 | Demo Site Engineer P1 | In progress | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-1 | 2026-09-01 | S25WRJ01-ACT-03 | Pump house | RCC concreting | 2026-09-21 | 2026-09-21 | 2026-09-25 | m3 | 240 | Blocked | Mobilise one crane and 150 m2 shuttering. | Demo Construction Lead P1 | 2026-09-23 | Mobilise the listed resource and confirm readiness before start. | S25WRJ01-DEC-03 | Demo Site Engineer P1 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-2 | 2026-09-01 | S25WRJ01-ACT-04 | Treatment plant | Earth excavation | 2026-09-28 | 2026-09-28 | 2026-09-30 | m3 | 260 | Ready | Reserve one excavator and two dumpers. | Demo Construction Lead P1 | 2026-09-27 | Mobilise the listed resource and confirm readiness before start. | S25WRJ01-DEC-04 | Demo Site Engineer P1 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-ACT-01 | Canal headworks | RCC concreting | 2026-09-07 | 2026-09-07 | 2026-09-11 | m3 | 225 | Ready | No current shortage; resolved test item. | Demo Construction Lead P2 | 2026-09-06 | No further support; completed. | S25WJH01-DEC-01 | Demo Site Engineer P2 | Completed | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-2 | 2026-09-01 | S25WJH01-ACT-02 | Canal reach | RCC concreting | 2026-09-14 | 2026-09-14 | 2026-09-18 | m3 | 245 | At risk | One standby concrete pump required. | Demo Construction Lead P2 | 2026-09-13 | Mobilise the listed resource and confirm readiness before start. | S25WJH01-DEC-02 | Demo Site Engineer P2 | In progress | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-1 | 2026-09-01 | S25WJH01-ACT-03 | Cross regulator | RCC concreting | 2026-09-21 | 2026-09-21 | 2026-09-25 | m3 | 265 | Blocked | Mobilise one crane and 150 m2 shuttering. | Demo Construction Lead P2 | 2026-09-23 | Mobilise the listed resource and confirm readiness before start. | S25WJH01-DEC-03 | Demo Site Engineer P2 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-2 | 2026-09-01 | S25WJH01-ACT-04 | Pump station | Earth excavation | 2026-09-28 | 2026-09-28 | 2026-09-30 | m3 | 285 | Ready | Reserve one excavator and two dumpers. | Demo Construction Lead P2 | 2026-09-27 | Mobilise the listed resource and confirm readiness before start. | S25WJH01-DEC-04 | Demo Site Engineer P2 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-ACT-01 | Service reservoir | RCC concreting | 2026-09-07 | 2026-09-07 | 2026-09-11 | m3 | 250 | Ready | No current shortage; resolved test item. | Demo Construction Lead P3 | 2026-09-06 | No further support; completed. | S25WMP01-DEC-01 | Demo Site Engineer P3 | Completed | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-2 | 2026-09-01 | S25WMP01-ACT-02 | Distribution zone | RCC concreting | 2026-09-14 | 2026-09-14 | 2026-09-18 | m3 | 270 | At risk | One standby concrete pump required. | Demo Construction Lead P3 | 2026-09-13 | Mobilise the listed resource and confirm readiness before start. | S25WMP01-DEC-02 | Demo Site Engineer P3 | In progress | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-1 | 2026-09-01 | S25WMP01-ACT-03 | Pump house | RCC concreting | 2026-09-21 | 2026-09-21 | 2026-09-25 | m3 | 290 | Blocked | Mobilise one crane and 150 m2 shuttering. | Demo Construction Lead P3 | 2026-09-23 | Mobilise the listed resource and confirm readiness before start. | S25WMP01-DEC-03 | Demo Site Engineer P3 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-2 | 2026-09-01 | S25WMP01-ACT-04 | Water treatment plant | Earth excavation | 2026-09-28 | 2026-09-28 | 2026-09-30 | m3 | 310 | Ready | Reserve one excavator and two dumpers. | Demo Construction Lead P3 | 2026-09-27 | Mobilise the listed resource and confirm readiness before start. | S25WMP01-DEC-04 | Demo Site Engineer P3 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-ACT-01 | Cooling water structure | RCC concreting | 2026-09-07 | 2026-09-07 | 2026-09-11 | m3 | 275 | Ready | No current shortage; resolved test item. | Demo Construction Lead P4 | 2026-09-06 | No further support; completed. | S26BBI01-DEC-01 | Demo Site Engineer P4 | Completed | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-2 | 2026-09-01 | S26BBI01-ACT-02 | Utility corridor | RCC concreting | 2026-09-14 | 2026-09-14 | 2026-09-18 | m3 | 295 | At risk | One standby concrete pump required. | Demo Construction Lead P4 | 2026-09-13 | Mobilise the listed resource and confirm readiness before start. | S26BBI01-DEC-02 | Demo Site Engineer P4 | In progress | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-1 | 2026-09-01 | S26BBI01-ACT-03 | Pump foundation | RCC concreting | 2026-09-21 | 2026-09-21 | 2026-09-25 | m3 | 315 | Blocked | Mobilise one crane and 150 m2 shuttering. | Demo Construction Lead P4 | 2026-09-23 | Mobilise the listed resource and confirm readiness before start. | S26BBI01-DEC-03 | Demo Site Engineer P4 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-2 | 2026-09-01 | S26BBI01-ACT-04 | Service building | Earth excavation | 2026-09-28 | 2026-09-28 | 2026-09-30 | m3 | 335 | Ready | Reserve one excavator and two dumpers. | Demo Construction Lead P4 | 2026-09-27 | Mobilise the listed resource and confirm readiness before start. | S26BBI01-DEC-04 | Demo Site Engineer P4 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-ACT-01 | Transformer foundation | RCC concreting | 2026-09-07 | 2026-09-07 | 2026-09-11 | m3 | 300 | Ready | No current shortage; resolved test item. | Demo Construction Lead P5 | 2026-09-06 | No further support; completed. | S26PRJ01-DEC-01 | Demo Site Engineer P5 | Completed | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-2 | 2026-09-01 | S26PRJ01-ACT-02 | Cable trench | RCC concreting | 2026-09-14 | 2026-09-14 | 2026-09-18 | m3 | 320 | At risk | One standby concrete pump required. | Demo Construction Lead P5 | 2026-09-13 | Mobilise the listed resource and confirm readiness before start. | S26PRJ01-DEC-02 | Demo Site Engineer P5 | In progress | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-1 | 2026-09-01 | S26PRJ01-ACT-03 | Control room | RCC concreting | 2026-09-21 | 2026-09-21 | 2026-09-25 | m3 | 340 | Blocked | Mobilise one crane and 150 m2 shuttering. | Demo Construction Lead P5 | 2026-09-23 | Mobilise the listed resource and confirm readiness before start. | S26PRJ01-DEC-03 | Demo Site Engineer P5 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-2 | 2026-09-01 | S26PRJ01-ACT-04 | Switchyard road | Earth excavation | 2026-09-28 | 2026-09-28 | 2026-09-30 | m3 | 360 | Ready | Reserve one excavator and two dumpers. | Demo Construction Lead P5 | 2026-09-27 | Mobilise the listed resource and confirm readiness before start. | S26PRJ01-DEC-04 | Demo Site Engineer P5 | Not started | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.

## Daily MOM
9. Daily MOM
Project code | S25WRJ01 |  | Total actions | 4 |  | Overdue actions | 1
Review date | 2026-09-20 |  | Open actions | 3
Meeting date | 2026-09-20 |  | Closed actions | 1
Enter data below. Blue text = editable. Grey cells = calculated. Dates: dd-mmm-yy. Money: INR lakh.
Keep stable IDs. Blank means unknown; enter zero only if confirmed. Filter the table separately from the project selector.
FICTIONAL TEST DATA — all records and values are invented solely for system testing.
Test review date: 20-Sep-2026. September dates are scenario dates, not real commitments. Replace these records before live use.
One row per action. Repeat the meeting reference/date for its actions. Open counts include In progress and On hold.
Overdue compares target closure with the Review date above. Enter Actual closure date and closure remarks before marking Closed.
Project code | Site / location | Meeting reference | Meeting date | Meeting chaired by | Participants | Item / action ID | Category | Discussion point / issue | Decision / instruction given | Agreed action | Responsible owner | Target closure date | Present Status | Progress / closure remarks | Actual closure date | MD escalation required | Linked Decision ID | Last updated | Source / entry notes
S25WRJ01 | P1-SITE-1 | S25WRJ01-MOM-20260920 | 2026-09-20 | Demo Project Head P1 | Demo Construction Lead P1, Demo Planning Lead P1, Demo Finance Lead P1 | S25WRJ01-MOM-A1 | Construction | Review completed pour | Accept completion evidence and close. | Record completion of the test item. | Demo Action Owner 1 P1 | 2026-09-20 | Closed | Demo completion checked at meeting. | 2026-09-20 | NO | S25WRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-2 | S25WRJ01-MOM-20260920 | 2026-09-20 | Demo Project Head P1 | Demo Construction Lead P1, Demo Planning Lead P1, Demo Finance Lead P1 | S25WRJ01-MOM-A2 | Liability | Review overdue vendor release | Implement agreed action and report against target date. | Resolve vendor payment. | Demo Action Owner 2 P1 | 2026-09-18 | In progress | Carry-forward action overdue; payment documentation pending. | Not yet occurred | YES | S25WRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. Carry-forward commitment from the 15-Sep meeting.
S25WRJ01 | P1-SITE-1 | S25WRJ01-MOM-20260920 | 2026-09-20 | Demo Project Head P1 | Demo Construction Lead P1, Demo Planning Lead P1, Demo Finance Lead P1 | S25WRJ01-MOM-A3 | Engineering | Resolve drawing revision | Implement agreed action and report against target date. | Resolve drawing revision. | Demo Action Owner 3 P1 | 2026-09-24 | Open | Owner assigned; follow-up required. | Not yet occurred | YES | S25WRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WRJ01 | P1-SITE-2 | S25WRJ01-MOM-20260920 | 2026-09-20 | Demo Project Head P1 | Demo Construction Lead P1, Demo Planning Lead P1, Demo Finance Lead P1 | S25WRJ01-MOM-A4 | Resources | Mobilise next-week crew | Implement agreed action and report against target date. | Resolve crew shortage. | Demo Action Owner 4 P1 | 2026-09-25 | On hold | Owner assigned; follow-up required. | Not yet occurred | YES | S25WRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-1 | S25WJH01-MOM-20260920 | 2026-09-20 | Demo Project Head P2 | Demo Construction Lead P2, Demo Planning Lead P2, Demo Finance Lead P2 | S25WJH01-MOM-A1 | Construction | Review completed pour | Accept completion evidence and close. | Record completion of the test item. | Demo Action Owner 1 P2 | 2026-09-20 | Closed | Demo completion checked at meeting. | 2026-09-20 | NO | S25WJH01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-2 | S25WJH01-MOM-20260920 | 2026-09-20 | Demo Project Head P2 | Demo Construction Lead P2, Demo Planning Lead P2, Demo Finance Lead P2 | S25WJH01-MOM-A2 | Liability | Review overdue vendor release | Implement agreed action and report against target date. | Resolve vendor payment. | Demo Action Owner 2 P2 | 2026-09-18 | In progress | Carry-forward action overdue; payment documentation pending. | Not yet occurred | YES | S25WJH01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. Carry-forward commitment from the 15-Sep meeting.
S25WJH01 | P2-SITE-1 | S25WJH01-MOM-20260920 | 2026-09-20 | Demo Project Head P2 | Demo Construction Lead P2, Demo Planning Lead P2, Demo Finance Lead P2 | S25WJH01-MOM-A3 | Engineering | Resolve drawing revision | Implement agreed action and report against target date. | Resolve drawing revision. | Demo Action Owner 3 P2 | 2026-09-24 | Open | Owner assigned; follow-up required. | Not yet occurred | YES | S25WJH01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WJH01 | P2-SITE-2 | S25WJH01-MOM-20260920 | 2026-09-20 | Demo Project Head P2 | Demo Construction Lead P2, Demo Planning Lead P2, Demo Finance Lead P2 | S25WJH01-MOM-A4 | Resources | Mobilise next-week crew | Implement agreed action and report against target date. | Resolve crew shortage. | Demo Action Owner 4 P2 | 2026-09-25 | On hold | Owner assigned; follow-up required. | Not yet occurred | YES | S25WJH01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-1 | S25WMP01-MOM-20260920 | 2026-09-20 | Demo Project Head P3 | Demo Construction Lead P3, Demo Planning Lead P3, Demo Finance Lead P3 | S25WMP01-MOM-A1 | Construction | Review completed pour | Accept completion evidence and close. | Record completion of the test item. | Demo Action Owner 1 P3 | 2026-09-20 | Closed | Demo completion checked at meeting. | 2026-09-20 | NO | S25WMP01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-2 | S25WMP01-MOM-20260920 | 2026-09-20 | Demo Project Head P3 | Demo Construction Lead P3, Demo Planning Lead P3, Demo Finance Lead P3 | S25WMP01-MOM-A2 | Liability | Review overdue vendor release | Implement agreed action and report against target date. | Resolve vendor payment. | Demo Action Owner 2 P3 | 2026-09-18 | In progress | Carry-forward action overdue; payment documentation pending. | Not yet occurred | YES | S25WMP01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. Carry-forward commitment from the 15-Sep meeting.
S25WMP01 | P3-SITE-1 | S25WMP01-MOM-20260920 | 2026-09-20 | Demo Project Head P3 | Demo Construction Lead P3, Demo Planning Lead P3, Demo Finance Lead P3 | S25WMP01-MOM-A3 | Engineering | Resolve drawing revision | Implement agreed action and report against target date. | Resolve drawing revision. | Demo Action Owner 3 P3 | 2026-09-24 | Open | Owner assigned; follow-up required. | Not yet occurred | YES | S25WMP01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S25WMP01 | P3-SITE-2 | S25WMP01-MOM-20260920 | 2026-09-20 | Demo Project Head P3 | Demo Construction Lead P3, Demo Planning Lead P3, Demo Finance Lead P3 | S25WMP01-MOM-A4 | Resources | Mobilise next-week crew | Implement agreed action and report against target date. | Resolve crew shortage. | Demo Action Owner 4 P3 | 2026-09-25 | On hold | Owner assigned; follow-up required. | Not yet occurred | YES | S25WMP01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-1 | S26BBI01-MOM-20260920 | 2026-09-20 | Demo Project Head P4 | Demo Construction Lead P4, Demo Planning Lead P4, Demo Finance Lead P4 | S26BBI01-MOM-A1 | Construction | Review completed pour | Accept completion evidence and close. | Record completion of the test item. | Demo Action Owner 1 P4 | 2026-09-20 | Closed | Demo completion checked at meeting. | 2026-09-20 | NO | S26BBI01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-2 | S26BBI01-MOM-20260920 | 2026-09-20 | Demo Project Head P4 | Demo Construction Lead P4, Demo Planning Lead P4, Demo Finance Lead P4 | S26BBI01-MOM-A2 | Liability | Review overdue vendor release | Implement agreed action and report against target date. | Resolve vendor payment. | Demo Action Owner 2 P4 | 2026-09-18 | In progress | Carry-forward action overdue; payment documentation pending. | Not yet occurred | YES | S26BBI01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. Carry-forward commitment from the 15-Sep meeting.
S26BBI01 | P4-SITE-1 | S26BBI01-MOM-20260920 | 2026-09-20 | Demo Project Head P4 | Demo Construction Lead P4, Demo Planning Lead P4, Demo Finance Lead P4 | S26BBI01-MOM-A3 | Engineering | Resolve drawing revision | Implement agreed action and report against target date. | Resolve drawing revision. | Demo Action Owner 3 P4 | 2026-09-24 | Open | Owner assigned; follow-up required. | Not yet occurred | YES | S26BBI01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26BBI01 | P4-SITE-2 | S26BBI01-MOM-20260920 | 2026-09-20 | Demo Project Head P4 | Demo Construction Lead P4, Demo Planning Lead P4, Demo Finance Lead P4 | S26BBI01-MOM-A4 | Resources | Mobilise next-week crew | Implement agreed action and report against target date. | Resolve crew shortage. | Demo Action Owner 4 P4 | 2026-09-25 | On hold | Owner assigned; follow-up required. | Not yet occurred | YES | S26BBI01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-1 | S26PRJ01-MOM-20260920 | 2026-09-20 | Demo Project Head P5 | Demo Construction Lead P5, Demo Planning Lead P5, Demo Finance Lead P5 | S26PRJ01-MOM-A1 | Construction | Review completed pour | Accept completion evidence and close. | Record completion of the test item. | Demo Action Owner 1 P5 | 2026-09-20 | Closed | Demo completion checked at meeting. | 2026-09-20 | NO | S26PRJ01-DEC-01 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-2 | S26PRJ01-MOM-20260920 | 2026-09-20 | Demo Project Head P5 | Demo Construction Lead P5, Demo Planning Lead P5, Demo Finance Lead P5 | S26PRJ01-MOM-A2 | Liability | Review overdue vendor release | Implement agreed action and report against target date. | Resolve vendor payment. | Demo Action Owner 2 P5 | 2026-09-18 | In progress | Carry-forward action overdue; payment documentation pending. | Not yet occurred | YES | S26PRJ01-DEC-02 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records. Carry-forward commitment from the 15-Sep meeting.
S26PRJ01 | P5-SITE-1 | S26PRJ01-MOM-20260920 | 2026-09-20 | Demo Project Head P5 | Demo Construction Lead P5, Demo Planning Lead P5, Demo Finance Lead P5 | S26PRJ01-MOM-A3 | Engineering | Resolve drawing revision | Implement agreed action and report against target date. | Resolve drawing revision. | Demo Action Owner 3 P5 | 2026-09-24 | Open | Owner assigned; follow-up required. | Not yet occurred | YES | S26PRJ01-DEC-03 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.
S26PRJ01 | P5-SITE-2 | S26PRJ01-MOM-20260920 | 2026-09-20 | Demo Project Head P5 | Demo Construction Lead P5, Demo Planning Lead P5, Demo Finance Lead P5 | S26PRJ01-MOM-A4 | Resources | Mobilise next-week crew | Implement agreed action and report against target date. | Resolve crew shortage. | Demo Action Owner 4 P5 | 2026-09-25 | On hold | Owner assigned; follow-up required. | Not yet occurred | YES | S26PRJ01-DEC-04 | 2026-09-20 | FICTIONAL TEST DATA. All people, quantities, money, dates and statuses are invented; not project records.